## Blad1
Systembolaget process | Oxfam Recommendations | Systembolaget action and time line | Responsibility | Human rights impacts and outcomes | Monitoring | Status | Added actions
Capacity building internally | Ensure that prices of wines enable all appropriate costs for ensuring decent working conditions to be met by: • Ensuring that buyers receive training to understand the impact of Systembolaget’s purchasing practices and prices on their suppliers’ ability to respect labour rights in their operations and supply chains. • Ensuring that buyers receive training to understand the specific human rights risks for Italy and the different wine regions. • Ensuring that buyers have access to information to judge what reasonable costs of production are in the various Italian wine producing regions. | We have developed a three part internal capacity building program which consists of: 1. Annual training for all buyers and category managers on how purchasing practices impacts human rights in our supply chain. 2. Annual training for buyers and category managers on specific human rights risks for their respective origins and product category. 3. Share aggregated sustainability data from our Sustainability Platform with relevant internal roles, for example buyers and category managers. This will be implemented in full before end of 2021. | Head of Sustainable Sourcing, Head of Assortment, Head of Purchasing | Decreasing the risk of price points that increases the risk for human rights violations connected to forced labour, low wages, excessive working hours, health and safety risks | Monitor capacity building in three steps; immediate learnings, behavioural change and impact | All the trainings have been adapted to include all sustainability aspects and not only focus on human rights. 1.The annual training for the buyers and category managers for 2022 was in February together with ETI Sweden. 2. Intitial Individual trainings were held with buyers and category managers during Q4 2021 to gather a better understanding of their needs and expectations. A survey after trainings showed that the buyers considers dialogue with impirters and producers highly important and a potential for further work, they want more sustainability information to have better dialogue with importers and producers and they will apply a risk perspective in their future work. 3. Aggregated data has been shared with buyers and category managers during their individual meetings while we are waiting for an automated way of sharing information. We have a created an annual process and timeline for these trainings to ensure consistency | The Nordic Alcoholic Monopolies (NAM) have issued an report by KPMG that looks at legislated minimum wage, calculated living wage, production cost and level of freedom of association in 23 of our biggest sourcing countries. The idea is to issue these reports annually. Systemblaget will integrate these reports into our internal capaciuty building program to ensure that there is a better knowledge within both purchasing and sustainability departments wages within our biggest sourcing countries and use that as a part of setting price points and minimize our negative impact on the value chain . | Explain how this will reduce the risk, how will the staff use this information. What effect will it have on for exmaple price, risks. Measure number producer (is it decreasing due to hgher demands relted to HR). Better link the report to the purchasing process/internal capacity building
Capacity building supply chain | Educate first tier suppliers and sub-suppliers about human rights risks in their supply chain and how they can prevent and mitigate risks through their purchasing practices and actions. Systembolaget depends more in its suppliers to ensure Systembolaget is limited in its direct contact with producers and growers. • Use the Sustainability Platform as a means to educate suppliers on human rights impacts and possibilities to prevent and mitigate such impacts. • Provide training to buyers at first tier suppliers on the impact of their company’s purchasing practices and prices on their suppliers’ ability to respect labour rights in their operations and supply chains. • Work with suppliers to provide training for workers - as well as employers - on labour rights and laws. | The capacity building program developed for Systembolaget staff (Listed above) will also be made available for our importers We will also compile a capacity building program for producers on the UNGPs and our most salient human rights risks together with the various organizations we collaborate with such as amfori BSCI, Stronger Together, IUF and Unionen. Example of topics; grievance mechanism, female workers, responsible recruitment, freedom of association. Both of these actions will be implemented by Q3 2021. | Head of Sustainable Sourcing | Enable and equip our business partners to further adress human rights risks in their supply chains and thereby increase the risk identification, impact and change | Monitor capacity building in three steps; immediate learnings, behavioural change and impact | All the trainings have been adapted to include all sustainability aspects and not only focus on human rights. 1.The annual training for the importers will be held in Q3 together with ETI Sweden 2. We will start an annual process for individual trainings/meetings for importers to ensure a joint understanding of what HRDD entails and how the importers should adress it, both in terms in due diligence process but also purchasing processes. These trainings will focus on HRDD in practice and our environmental strategic focus areas. The annual process will also include follow-up surveys to measure the impact of the trainings. During 2022, Systembolaget will meet with 27 importers that represents 80% of our total sales volumes during 2022. By targeting the bigger importers in terms of volume we also cover the biggest risk regions. In addition to that we will continue to host group HREDD-workshops for our specific regions and risks. 3. Data from the Sustainability Platform will be shared during importers individual meetings while we are waiting for an automated way of sharing information. The capacity building program is finalized and published on our importers portal to facilitate their work with their producers We have a created an annual process and timeline for these trainings to ensure consistency. | During Q1 2022 we also arranged trainings for Italian producers on responsible recruitment together with the other Nordic monopolies and Stronger Together, which is an organization specialized in modern slavery. The training is split in two sections. One general introduction and one workshop format for individual producers. So far 44 producers have attended. The trainings were followed up by a survey. Out of 11 respondees 100% stated that their knowledges had increased, 9 replied that they will include modern slavery in their buying dialogue going forward and that they will promotoe trainings o modern slavery in their supply chains. | Clear what the indiviudal meetings consist of.How do we monitor and measure the impact of HR risks after the importers (importance of creating an annual process for questionnaire and evaluation of chnages). Expain how 80% covers the high risk areas or not (for example Tre Svampar)
Purchasing practices | 1/ Ensure that human rights concerns are taken into account in tender documents by requiring tier one suppliers who win tenders to account for how ethical production costs were ensured. 2/ Add questions on ethical production costs to the Sustainability Platform. 3/ Conduct a stakeholder engagement dialogue on prices and discuss how greater transparency on price-setting and relationship with cost of sustainable production (including labour conditions that respect human rights) throughout the supply chain can be assured. • Introduce and formalise a system within Systembolaget’s due diligence process which flags any price bracket in tenders which has remained the same for a certain period. • Develop a system within Systembolaget’s due diligence process which flags when national/regional changes in collective wage agreements/ minimum wages occur. • Consider developing a system within Systembolaget’s due diligence process which flags any significant price drop in the fixed assortment. | As a part of Systembolaget’s strategy for 2020-2023 a new framework for responsible sourcing is being developed. The purpose of the framework is to ensure that our purchasing process minimizes risks for human rights violations where we have an impact. The framework will for example contain: - Systematic overview of price brackets in our launching plan for all assortments where labour cost is taken into account - Overview of risk based requirements for all the assortments - Guidelines of relevant certification schemes The framework is being implemented during 2021. | Head of Sustainable Sourcing, Head of Assortment, Head of Purchasing | Decreasing the risk of price points that increases the risk for human rights violations connected to forced labour, low wages, excessive working hours, health and safety risks | Framework will contain a function for deviances to the framework. This will be measured and assessed annually to assure progress. | Our framework for responsible sourcing was published the 15th if September 2021. Read it here (länk). We asked for feedback on the framework from our suppliers and closed that window by the 15th of January 2022. We are currently conducting the annual update. The framework creates a systemized approach in our purchasing process concerning sustainability and human rights. Systembolaget belive it is crucial that we connect the business to sustainability and therefore the ambitions stated in the framework are correlated to our KPIs regarding human rights. This ensures that the different departments are working towards and are measured on the same things. | Together with the NAM we have initiated a common work on living wage in our supply chains. The KPMG report will be a baseline for that work and in addition to that we organized an importers training on living wage. Next steps are: 1.) Conduct a pilot together with importers and proudcers on how the gap between minimum and living wage can be closed during 2022. 2.) Based upon the findings from the report create a NAM road map on a systematic work towards living wage. We are looking into to how we can integrate a HREDD approach to our purchasing process. One example is that we will start conducting random checks of new launches connected to relevant risks during Q2 2022, for example that tenders should require suppliers to account for ethical production costs.
Business incentives | Encourage long-term perspectives and investments to address sustainability challenges in supply chain by: • Give preferential treatment to wines which can be considered ‘good performers’ in terms of the respect of human rights. | Systembolaget is currently developing a new communication towards consumers to enable consumers to make more sustainable choices. The selection of products receiving this communication will be based upon the risk assessment in our Sustainability platform as well as other sustainability aspects. This will be initiated in Q1 2022. | Head of Sustainable Sourcing, Head of Assortment, Head of Purchasing, Head of Sustainability and |  | Number of products within the selection of sustainable choice. | The new label will launched 1st of March 2022. | Systembolaget will start conducting random checks of "Sustainable choice" during Q3 2022
Risk assessment and supply chain | Ensure that more rigorous due diligence processes also apply to products in the ordering assortment. | We are extending our due diligence process to all products in the ordering assortment from the origins where our most salient risks are the most prevalent. Goal is for this to be started by Q1 2022 and thereafter we will continuously add more products and regions to the process. | Head of Sustainable Sourcing | Add a salient risk perspective to the due diligence process to better identify risks independently of sales volume. | Will be followed-up and revised within the strategic focus area of sustainable supply chain annualy | Process was initiaded in Q3 2021 and the follow-up from that process will be started during Q2 2022.
| Expand SAQs in the Sustainability Platform related to most salient human rights risk, for example recruitment practices, migrant and female workers | The Sustainability Platform is still being developed and we will incorporate the extended SAQs during 2022 or as soon as it is technically possible. We do however consider this an on going work that must be updated continously as our supply chain and its' risks changes. | Head of Sustainable Sourcing | Expanding the SAQs will provide better input on potential human rights risk |  | Our platform will be undergoing fundamental changes and therefore we are not able to make these updates. However, we are in close collaboration with our service provider to ensure this wil be included in the updates version. | During 2022, Systembolaget is reassesing our current due diligence work in our supply chains to better align med with OECD guidelines for HRDD for businesses. The ambition is that this will ensure better risk idenfication and risk mitigating processes with focus on salient risks and even more transparency. By publicly sharing those risks and working accordingly to the OECD model our ambition is that it will create better focus and alignemnt in the industry. For example, this approcah is also incorporated in the NAM Social Road map. We will publich our new approach as well as how we intend to measure our impact in Q3 2022.
| Ensure that all workers in Systembolaget’s Italian wine supply chain are adequately represented and have access to a grievance mechanism that meets the standards outlined in the UNGPs . Ensuring that workers are adequately represented and have access to a grievance mechanism should be done by: • Working with suppliers, local trade unions and the IUF/ FLAI-CGIL to ensure that farms and wineries understand the benefits of trade unions and how they can help ensure they are compliant with Systembolaget’s Code of Conduct. • Developing a strategy with suppliers to build trust in trade unions over time so that all workers, including migrant workers, are properly represented. Guidance on how to do this is available from the Ethical Trading Initiative . • Signaling public support for the work of trade unions in Italy and consult on possible Systembolaget advocacy efforts. | Systembolaget is extending our work with Unionen and IUF in Italy during 2021 with the intention of strengthening the unionization in our supply chain. This includes producer and importer meetings focused specifically on the importance of trade unions to be included in an progressive work with human rights. We do consider this a relevant topic for several other regions as well and will utilize the MoU with IUf and Unionen to speak to importers for other regions as a part of the capacity building program mentioned above. This is an ongoing work but the official start for Italy will take place in May 2021. | Head of Sustainable Sourcing | Increase knowledge of and incentivize freedom of association in our supply chains to enable more workers to unionize and raise concerns | Monitor capacity building in three steps; immediate learnings, behavioural change and impact. Track share of unionized producers and farms annually | In December, Systembolaget met with the three Italian unions that are affiliated with IUF and a part of the MoU to discuss the implementation of the MoU in Italy. A new meeting together with unions is planned for September 2022.
| Ensure that all workers in Systembolaget’s Italian wine supply chain are adequately represented and have access to a grievance mechanism that meets the standards outlined in the UNGPs . Expand the SAQs to assess the lack of access to remedy, including assessing whether workers have adequate options available to raise complaints about their treatment | We are testing a new workers’ voice system which allows workers to answer questions anonymously regarding their working situation over the phone. The agrregated results can be used as a foundation for dialogue between the employer and the workers representatives. The tests are started during the summer 2021 with the intention of scaling up the solution continuously going forward. There is a question on access to grievance mechanism in the SAQs but by moving this question to the general questions part will allow input from all producers and farms regardless of region and the assumed risk. This change will be done in Q3 2021 to allow us to follow up on the high-risk process for the ordering assortment. | Head of Sustainable Sourcing | Increase knowledge of the existence of grievance mechanisms in our supply chains. Provide business partners with an hands-on way for workers to raise concerns in a safe way. | Test will be evaluated after one year (Q3 2022) to assess further roll-out. SAQ question will be tracked annually | The tests are still ongoing. We have updated the SAQ with a question regarding grievance mechanism. According to current numbers, 512 out of the 1298 supply chain actors that ahve recived the question, have stated they have a grievance mechanism.
| Table 15. Prioritisation of identified human rights impacts | Include this framework in future development and updates of processes | Head of Sustainable Sourcing | All mentioned in table | N/A